CCAC Processing Timeline (Revised 04/20/09)

4/1 – 6/15	CCS work plan analyses underway

4/15 – 5/18	Public comment period for draft impact assessment report

5/18 – 5/22	DEP Comment Response document; preparation and approval of final report

5/22 – 5/28	Printing final impact assessment report

5/29	Delivery of final impact assessment report to General Assembly, Governor and public

6/1 – 6/15	Phased completion of work plan analyses by CCS

6/15	Initiation of macroeconomic modeling

6/1 – 6/28	Concurrent subcommittee review and scoring of work plans

6/29	Subcommittees make recommendations to full CCAC

6/29 – 7/19	CCAC reviews subcommittee recommendations

7/20	CCAC makes recommendations to DEP

7/20 – 7/24	DEP integration of CCAC final recommendations

7/25 - 8/7 	OETD & Policy Review (concurrent)

8/10 - 8/14 	CCAC Review

8/14 - 8/16	OETD Compiles & Reviews Comments

8/17 - 8/21 	OETD & Policy Comment Integration and Final Review w/o macroeconomic analysis

8/24 - 8/28	Chief Counsel & OA Review (concurrent) w/o macroeconomic analysis

9/1	Macroeconomic analysis complete

9/1 – 9/14	DEP & CCAC review of macroeconomic analysis

9/15	CCAC provides comments to DEP

9/15 – 9/22	DEP incorporates comments and macroeconomic assessment into action plan

9/22 – 10/8	DEP final approval process and printing

9/29 	Bulletin notice prepared with link (not live until 10/9) to final report

10/9	Action Plan delivered to General Assembly, Governor’s Office, posted on DEP website

TBD	30 day public comment period concurrent with regional public meetings; comment response document prepared as addendum to Action Plan

| April |  | May |  | June |
| --- | --- | --- | --- | --- |
| Su | M | Tu | W | Th | F | Sa |  | Su | M | Tu | W | Th | F | Sa |  | Su | M | Tu | W | Th | F | Sa |
|  |  |  | 1 | 2 | 3 | 4 |  |  |  |  |  |  | 1 | 2 |  |  | 1 | 2 | 3 | 4 | 5 | 6 |
| 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 26 | 27 | 28 | 29 | 30 |  |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | 28 | 29 | 30 |  |  |  |  |
|  |  |  |  |  |  |  |  | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| July |  | August |  | September |
| Su | M | Tu | W | Th | F | Sa |  | Su | M | Tu | W | Th | F | Sa |  | Su | M | Tu | W | Th | F | Sa |
|  |  |  | 1 | 2 | 3 | 4 |  |  |  |  |  |  |  | 1 |  |  |  | 1 | 2 | 3 | 4 | 5 |
| 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| 26 | 27 | 28 | 29 | 30 | 31 |  |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 |  | 27 | 28 | 29 | 30 |  |  |  |
|  |  |  |  |  |  |  |  | 30 | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| October |  | November |  | December |
| Su | M | Tu | W | Th | F | Sa |  | Su | M | Tu | W | Th | F | Sa |  | Su | M | Tu | W | Th | F | Sa |
|  |  |  |  | 1 | 2 | 3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 1 | 2 | 3 | 4 | 5 |
| 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| 18 | 19 | 20 | 21 | 22 | 23 | 24 |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| 25 | 26 | 27 | 28 | 29 | 30 | 31 |  | 29 | 30 |  |  |  |  |  |  | 27 | 28 | 29 | 30 | 31 |  |  |

Dates in Red are Milestones; Dates in Orange are Existing CCAC Meeting Dates; Dates in Yellow are Holidays