## CCAC Timeline
CCAC Timeline of Duties
Project Name |  | PA Climate Change Advisory Committee
Company Name |  | PA Department of Environmental Protection
| Project Lead: | Sarah Hetznecker
| Today's Date: | 2008-11-04 |  | (vertical red line)
[42] | Start Date: | 2008-10-20 | 2008-10-20 | [6 empty] | 0 | 2008-10-20 | 2008-10-21 | 2008-10-22 | 2008-10-23 | 2008-10-24 | 2008-10-27 | 2008-10-28 | 2008-10-29 | 2008-10-30 | 2008-10-31 | 2008-11-03 | 2008-11-04 | 2008-11-05 | 2008-11-06 | 2008-11-07 | 2008-11-10 | 2008-11-11 | 2008-11-12 | 2008-11-13 | 2008-11-14 | 2008-11-17 | 2008-11-18 | 2008-11-19 | 2008-11-20 | 2008-11-21 | 2008-11-24 | 2008-11-25 | 2008-11-26 | 2008-11-27 | 2008-11-28 | 2008-12-01 | 2008-12-02 | 2008-12-03 | 2008-12-04 | 2008-12-05 | 2008-12-08 | 2008-12-09 | 2008-12-10 | 2008-12-11 | 2008-12-12 | 2008-12-15 | 2008-12-16 | 2008-12-17 | 2008-12-18 | 2008-12-19 | 2008-12-22 | 2008-12-23 | 2008-12-24 | 2008-12-25 | 2008-12-26 | 2008-12-29 | 2008-12-30 | 2008-12-31 | 2009-01-01 | 2009-01-02 | 2009-01-05 | 2009-01-06 | 2009-01-07 | 2009-01-08 | 2009-01-09 | 2009-01-12 | 2009-01-13 | 2009-01-14 | 2009-01-15 | 2009-01-16 | 2009-01-19 | 2009-01-20 | 2009-01-21 | 2009-01-22 | 2009-01-23 | 2009-01-26 | 2009-01-27 | 2009-01-28 | 2009-01-29 | 2009-01-30 | 2009-02-02 | 2009-02-03 | 2009-02-04 | 2009-02-05 | 2009-02-06 | 2009-02-09 | 2009-02-10 | 2009-02-11 | 2009-02-12 | 2009-02-13 | 2009-02-16 | 2009-02-17 | 2009-02-18 | 2009-02-19 | 2009-02-20 | 2009-02-23 | 2009-02-24 | 2009-02-25 | 2009-02-26 | 2009-02-27 | 2009-03-02 | 2009-03-03 | 2009-03-04 | 2009-03-05 | 2009-03-06 | 2009-03-09 | 2009-03-10 | 2009-03-11 | 2009-03-12 | 2009-03-13 | 2009-03-16 | 2009-03-17 | 2009-03-18 | 2009-03-19 | 2009-03-20 | 2009-03-23 | 2009-03-24 | 2009-03-25 | 2009-03-26 | 2009-03-27 | 2009-03-30 | 2009-03-31 | 2009-04-01 | 2009-04-02 | 2009-04-03 | 2009-04-06 | 2009-04-07 | 2009-04-08 | 2009-04-09 | 2009-04-10 | 2009-04-13 | 2009-04-14 | 2009-04-15 | 2009-04-16 | 2009-04-17 | 2009-04-20 | 2009-04-21 | 2009-04-22 | 2009-04-23 | 2009-04-24 | 2009-04-27 | 2009-04-28 | 2009-04-29 | 2009-04-30 | 2009-05-01 | 2009-05-04 | 2009-05-05 | 2009-05-06 | 2009-05-07 | 2009-05-08 | 2009-05-11 | 2009-05-12 | 2009-05-13 | 2009-05-14 | 2009-05-15 | 2009-05-18 | 2009-05-19 | 2009-05-20 | 2009-05-21 | 2009-05-22 | 2009-05-25 | 2009-05-26 | 2009-05-27 | 2009-05-28 | 2009-05-29 | 2009-06-01 | 2009-06-02 | 2009-06-03 | 2009-06-04 | 2009-06-05 | 2009-06-08 | 2009-06-09 | 2009-06-10 | 2009-06-11 | 2009-06-12 | 2009-06-15 | 2009-06-16 | 2009-06-17 | 2009-06-18 | 2009-06-19 | 2009-06-22 | 2009-06-23 | 2009-06-24 | 2009-06-25 | 2009-06-26 | 2009-06-29 | 2009-06-30 | 2009-07-01 | 2009-07-02 | 2009-07-03 | 2009-07-06 | 2009-07-07 | 2009-07-08 | 2009-07-09 | 2009-07-10 | 2009-07-13 | 2009-07-14 | 2009-07-15 | 2009-07-16 | 2009-07-17 | 2009-07-20 | 2009-07-21 | 2009-07-22 | 2009-07-23 | 2009-07-24 | 2009-07-27 | 2009-07-28 | 2009-07-29 | 2009-07-30 | 2009-07-31 | 2009-08-03 | 2009-08-04 | 2009-08-05 | 2009-08-06 | 2009-08-07 | 2009-08-10 | 2009-08-11 | 2009-08-12 | 2009-08-13 | 2009-08-14 | 2009-08-17 | 2009-08-18 | 2009-08-19 | 2009-08-20 | 2009-08-21 | 2009-08-24 | 2009-08-25 | 2009-08-26 | 2009-08-27 | 2009-08-28 | 2009-08-31 | 2009-09-01 | 2009-09-02 | 2009-09-03 | 2009-09-04 | 2009-09-07 | 2009-09-08 | 2009-09-09 | 2009-09-10 | 2009-09-11 | 2009-09-14 | 2009-09-15 | 2009-09-16 | 2009-09-17 | 2009-09-18
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2008-10-20: 2008-10-20; 2008-10-27: 2008-10-27; 2008-11-03: 2008-11-03; 2008-11-10: 2008-11-10; 2008-11-17: 2008-11-17; 2008-11-24: 2008-11-24; 2008-12-01: 2008-12-01; 2008-12-08: 2008-12-08; 2008-12-15: 2008-12-15; 2008-12-22: 2008-12-22; 2008-12-29: 2008-12-29; 2009-01-05: 2009-01-05; 2009-01-12: 2009-01-12; 2009-01-19: 2009-01-19; 2009-01-26: 2009-01-26; 2009-02-02: 2009-02-02; 2009-02-09: 2009-02-09; 2009-02-16: 2009-02-16; 2009-02-23: 2009-02-23; 2009-03-02: 2009-03-02; 2009-03-09: 2009-03-09; 2009-03-16: 2009-03-16; 2009-03-23: 2009-03-23; 2009-03-30: 2009-03-30; 2009-04-06: 2009-04-06; 2009-04-13: 2009-04-13; 2009-04-20: 2009-04-20; 2009-04-27: 2009-04-27; 2009-05-04: 2009-05-04; 2009-05-11: 2009-05-11; 2009-05-18: 2009-05-18; 2009-05-25: 2009-05-25; 2009-06-01: 2009-06-01; 2009-06-08: 2009-06-08; 2009-06-15: 2009-06-15; 2009-06-22: 2009-06-22; 2009-06-29: 2009-06-29; 2009-07-06: 2009-07-06; 2009-07-13: 2009-07-13; 2009-07-20: 2009-07-20; 2009-07-27: 2009-07-27; 2009-08-03: 2009-08-03; 2009-08-10: 2009-08-10; 2009-08-17: 2009-08-17; 2009-08-24: 2009-08-24; 2009-08-31: 2009-08-31; 2009-09-07: 2009-09-07; 2009-09-14: 2009-09-14
1 | Score GHG Reduction Options |  | 2008-11-05 | 2009-02-28 | 116 | 0% | 83 | 0 | 116 | bar: 2009-03-02 to 2009-06-12
1.1 | Subcommittee #1 |  | 2008-11-05 | 2009-02-28 | 116 | 0% | 83 | 0 | 116 | bar: 2009-03-02 to 2009-06-12
1.2 | Subcommittee #2 |  | 2008-11-05 | 2009-02-28 | 116 | 0% | 83 | 0 | 116 | bar: 2009-03-02 to 2009-06-12
1.3 | Subcommittee #3 |  | 2008-11-05 | 2009-02-28 | 116 | 0% | 83 | 0 | 116 | bar: 2009-03-02 to 2009-06-12
1.4 | Subcommittee #4 |  | 2008-11-05 | 2009-02-28 | 116 | 0% | 83 | 0 | 116 | bar: 2009-03-02 to 2009-06-12
1.5 | Subcommittee #5 |  | 2008-11-05 | 2009-02-28 | 116 | 0% | 83 | 0 | 116 | bar: 2009-03-02 to 2009-06-12
2 | Impacts Assessment |  | 2008-10-21 | 2009-07-27 | 280 | 4.416% | 200 | 12 | 268
2.1 | Comment on Scope of Work |  | 2008-10-21 | 2008-11-06 | 17 | 40% | 13 | 6 | 11
2.2 | Comment on Proposal |  | 2008-11-20 | 2008-12-06 | 17 | 0% | 12 | 0 | 17
2.3 | CCAC Comment on Draft |  | 2009-03-15 | 2009-04-13 | 30 | 0% | 21 | 0 | 30
2.4 | Outreach During Public Comment Period |  | 2009-04-15 | 2009-05-14 | 30 | 0% | 22 | 0 | 30
2.5 | DEP Integration of Public Comments and Final Draft |  | 2009-05-15 | 2009-06-28 | 45 | 0% | 31 | 0 | 45
2.6 | CCAC Review of Final Draft |  | 2009-06-28 | 2009-07-12 | 15 | 0% | 10 | 0 | 15
3 | Inventory |  | 2009-03-01 | 2009-04-02 | 33 | 0% | 24 | 0 | 33
3.1 | CCAC Review of Data Sources |  | 2009-03-01 | 2009-03-17 | 17 | 0% | 12 | 0 | 17
3.2 | CCAC Review of Draft Inventory |  | 2009-03-18 | 2009-04-03 | 17 | 0% | 13 | 0 | 17
4 | Climate Change Action Plan |  | 2009-01-15 | 2009-09-23 | 252 | 0% | 180 | 0 | 252
4.1 | Determine Reduction Goals |  | 2009-01-15 | 2009-06-08 | 145 | 0% | 103 | 0 | 145
4.2 | Determine Timeframes to Achieve Goals |  | 2009-01-15 | 2009-06-08 | 145 | 0% | 103 | 0 | 145
4.3 | Determine Consumption vs. Generation Model |  | 2009-01-15 | 2009-06-08 | 145 | 0% | 103 | 0 | 145
4.4 | DEP Drafts Plan |  | 2009-02-28 | 2009-04-28 | 60 | 0% | 42 | 0 | 60
4.5 | CCAC Comments on Draft |  | 2009-04-28 | 2009-06-17 | 51 | 0% | 37 | 0 | 51
4.6 | Outreach During Public Comment Period |  | 2009-05-16 | 2009-06-14 | 30 | 0% | 20 | 0 | 30
4.7 | DEP Responds to Comments, Prepares Final Draft |  | 2009-06-14 | 2009-07-28 | 45 | 0% | 32 | 0 | 45
4.8 | CCAC Reviews Final Draft |  | 2009-07-28 | 2009-08-26 | 30 | 0% | 22 | 0 | 30
4.9 | DEP Final Draft and Approval Process |  | 2009-08-26 | 2009-09-24 | 30 | 0% | 22 | 0 | 30
Note on A11: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on H11: Working Days Counts only Mon-Fri, using the NETWORKDAYS() formula. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached. Note: If the start date is later changed, the number of working days may also change.
Note on I11: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J11: Calendar Days Remaining This column is calculated by subtracted the Days Complete from the Duration.
Note on F11: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F13=MAX(E14:E17)-D13
Note on G11: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G13=SUMPRODUCT(F14:F17,G14:G17)/SUM(F14:F17) Note: If you insert rows, make sure that the calculation is updated correctly.
Note on E11: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on D11: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on J1: Limited Use Policy You may download this template free of charge, make archival copies, and customize the template for personal use or for your company use. The customized template (with your specific personal or company information) may be used and distributed within your company, but otherwise, this template or any document including or derived from this template may NOT be sold, distributed, or placed on a public server such as the internet without the express written permission of Vertex42 LLC. The copyright notice(s) within the spreadsheet may NOT be removed, deleted, or hidden. No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Some states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Somes states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.