## Slide 1: Orphan Well Grant Program (OWPG)
Information / Training
August 2024
Jessica Shirley, Acting Secretary
Josh Shapiro, Governor

## Slide 2
Orphan Well Plugging Grant
Title 1V Non-Discrimination Notice
Federal and State law prohibit discrimination on the basis of age, color, creed, mental and/or physical disability, gender identity, national origin, pregnancy, race, religion, sex, or sexual orientation. If you believe you have been discriminated against in any program, activity or facility as described above, or if you desire further information, please contact DEP’s Non-Discrimination Coordinator at ra-epnondiscrim@pa.gov.
For more information, please visit DEP’s web page on Non-Discrimination

## Slide 3
Orphan Well Plugging Grant
Infrastructure Investment and Jobs Act (IIJA)
Acts 96/136 (Orphan Well Plugging Grant)
  Chapter 28 of the Oil & Gas Act (58 PA.C.S. §§ 2801 et. seq.)

## Slide 4
Orphan Well Plugging Grant
Optional Checklist
  Pre-application
  Pre-plugging
  Plugging
  Post-plugging

## Slide 5
Pre-application
Eligible Well
  Abandoned_Orphan_Web - Report Viewer (pa.gov)
  Exclude IIJA Wells
PA Oil and Gas Mapping
  Well Type (select all), Well Status (DEP Orphan)

## Slide 6
Pre-application
Eligible Applicant
  Qualified Well Plugger
  Oil and Gas Compliance - Report Extracts (pa.gov)
Obtain UEI Number
  Go to SAM.gov to register

## Slide 7
Pre-application
Well Plugging and Restoration Agreement
  Landowner Consent Form
Visit Well
  Confirm location (take photo)
  Methane screening (required)
  Check for soil contamination

## Slide 8
Conditional Application Approval
Complete Grant Application
  15 days for approval/denial
    letter 3 days after
    Conditional per EID requirements
  Submit Environmental Information Documentation (EID) for ESA/NHPA Clearances

## Slide 9
Conditonal Application Approval
DOI Terms and Conditions
  Environmental Information Documentation
    Project Scope and Description
    ESA Clearances
    NHPA Clearances
      Package must be approved by DOI before NTP Issued

## Slide 10
Application Approval
Grant Agreement
  45 days awardee to sign
  DEP sign (executed)
  Notice to Proceed (NTP) issued

## Slide 11
Pre-plugging
Methane Measurement
  Methane Measurement Service Provider form
    Submitted pre-measurement
  Methane Measurement Report form
    All readings, submitted at end of project
SAP Vendor #

## Slide 12
Pre-plugging
Notice of Intent to Plug (NOI)
  Submit to Oil and Gas Inspector
  District office
  Copy ra-eporphangrant@pa.gov

## Slide 13
Plugging
Daily Log of Activities
  Submitted Weekly
Daily Electronic Briefing
  Brief e-mail, submitted daily

## Slide 14
Plugging
Davis Bacon Act Compliance
  Wage Determinations
    Sent to grantee with grant agreement
  Weekly Certified Payroll
    Submitted weekly to ra-eporphangrant@pa.gov

## Slide 15
Plugging
Tech Specs
Expectations
Oversight

## Slide 16
Post-Plugging
Certificate of Well Plugging
Methane Measurement Report
Orphan Well Completion Worksheet
Itemized Expenses for Reimbursement form

## Slide 17
Application

## Slide 18
Application

## Slide 19
Application

## Slide 20
Application

## Slide 21
Application

## Slide 22
Application

## Slide 23
Application

## Slide 24
Application

## Slide 25
Application

## Slide 26
Application

## Slide 27
Application

## Slide 28
Application

## Slide 29
Application

## Slide 30
Application

## Slide 31
Application

## Slide 32
Application

## Slide 33
Application

## Slide 34
Application

## Slide 35
Application

## Slide 36
Environmental Considerations
Chapter 102 Requirements (earth disturbance)
  < 5 acres total earth disturbance = E&S Plan
  Minimize disturbance, use BMPs, seed and mulch
  Site remediation: achieve ≥ 70% perennial vegetative cover

## Slide 37
Environmental Considerations
Chapter 105 Requirements (water obstructions and encroachments to streams, wetlands, etc.)
  Permitting (typically GP-8, sometimes Environmental Assessment for waived activities)
  Avoid and minimize, steel plates over culverts, temporary bridges, fiberglass or wood timber matting to reduce soil compaction

## Slide 38
Environmental Considerations
Water Withdrawals
  Prevent impingement & entrainment
  Prevent spread of aquatic invasive species
    Resources: PFBC and StopAquaticHitchHikers.Org
    Backflow preventer + Clean, Drain, Dry and/or Disinfect
Through-screen velocity ≤ ft/sec
Mesh size ≤ (floating) ≤ (submerged)
Recommend place inside coarse “trash rack” for debris
Clear leaves and debris regularly
Flex Hose
Ball check valve example (one-way flow)
Image credit: Tameson.com
Example intake screen
Image credit: Federal Screen Products, Inc.
Intake side
Pump/Tank side
Pumping
Pump Off

## Slide 39
Environmental Considerations
Control and disposal
  Fluids: brine, chemicals, drilling mud, water
  Reuse water when possible
  Contaminated soils - dispose at a certified facility
  Trash, well remnants, tanks, pipes, etc.
    Recycle when possible
    Historic properties – DEP will consult PHMC

## Slide 40
Environmental Considerations
PNDI Conservation Explorer Tool
  Federal law: Endangered Species Act (ESA)
  PA Law: Wild Resource Conservation Act, Fish & Boat Code, Game & Wildlife Code
  Resource agencies: USFWS, PFBC, PGC, DCNR
  Free account, submit projects free, $40 fee for final receipt

## Slide 41
Environmental Considerations
PA-SHARE Tool
  Federal law: Section 106 of National Historic Preservation Act (NHPA)
  PA Law: State History Code
  Resource agencies: PHMC's SHPO Office (state), ACHP (federal)
  Free account, submit projects free, receive receipt
Notes: Pennsylvania Historic and Museum Commission – State Historic Preservation Office (SHPO) or "The SHPO" as in "Officer" = the Executive Director of PHMC
ACHP = Advisory Council on Historic Preservation
Other consulting parties may include:
Tribal Historic Preservation Officers of federally recognized Indian Tribes (18 with historic presence in Pennsylvania), local historical societies, and other organizations with interests in cultural resource preservation.

## Slide 42
Additional Opportunities
IIJA Plugging Contracts
  Invitation to Bid (Low bid)
  Request for Proposal (Technically Qualified Well Plugging Contractor)
Methane Emissions Reduction Program (MERP)

## Slide 43
Additional Opportunities
Methane Emissions Reduction Program (MERP)
Marginal Conventional Well (MCW)
$420,000 for any single applicant within each application period
  $20,000 for each eligible well <or= 3,000 feet
  $35,000 for each eligible well > than 3,000 feet
Applicants: Operator of wells, Qualified Well Plugger, Third Party
MERP Small Operator Assistance: Operator of 10 or less wells
MERP General Assistance: Operator of 11 or more wells

## Slide 44: Joe Gaboff jgaboff@pa.gov Any further questions can be sent to ra-epoilandgas@pa.gov