## Sheet1
Funding Breakdown
Project Number | Title/Operator | County | Township | Completion Date (Anticipated) | Date Awarded | Anticipated Bid Opening Date | Project Acreage | Project Cost or Estimate | Title IV | 10% Set Aside | Title IV - ACSI | Title IV - Anthracite Area | Title IV - Metals Recovery | Collected Bond | Bond Forfeiture Program | Growing Greener
Projects Completed during Calendar Year 2004
AD 0634 | TRESCKOW SOUTH | Carbon | Banks | 2004-04-14 | 2004-04-14 |  | 2 | 391.15 | 391.15
AD 0672-2 | LOYALSOCK CREEK | Sullivan | Colley | 2004-07-28 | 2004-07-28 |  | 0.5 | 422.55 | 422.55
AD 0676-2 | TOMHICKEN | Luzerne | Sugarloaf | 2004-06-29 | 2004-06-29 |  | 0.2 | 421.74 | 421.74
AD 0725-1 | NORTH DONALDSON | Schuylkill | Frailey | 2004-10-20 | 2002-09-17 |  | 0.5 | 9559.8 | 9559.8
AD 0733 | LANSFORD N.E. | Carbon | Summit Hill | 2004-05-05 | 2004-04-21 |  | 0.2 | 4089.74 | 4089.74
AD 0736 | ARCHBALD MINE SHAFT | Lackawanna | Archbald | 2004-06-03 | 2004-05-26 |  | 0.2 | 3482.65 | 3482.65
AD 0739 | OLD BOSTON | Luzerne | Jenkins | 2004-07-08 | 2004-06-04 |  | 0.2 | 9631.54 | 9631.54
AD 0740 | SHAMOKIN SOUTH, II | Northumberland | Mount Carmel | 2004-04-12 | 2004-04-12 |  | 0.2 | 354.94 | 354.94
AD 0741 | BALTIMORE SHAFT | Luzerne | Larksville | 2004-05-20 | 2004-05-19 |  | 0.2 | 2582.56 | 2582.56
AD 0742 | SHAMOKIN SOUTH, I | Northumberland | Mount Carmel | 2004-04-09 | 2004-04-09 |  | 0.2 | 652.9 | 652.9
AD 0745 | SHERIDAN BANK | Schuylkill | Porter | 2004-03-31 | 2004-03-03 |  | 1 | 5717.76 | 5717.76
AD 0746 | SEAL WETLAND-HELLS KITCHEN | Luzerne | Butler | 2004-05-25 | 2004-05-10 |  | 2 | 2375.61 | 2375.61
AD 0748 | SELTZER WEST | Schuylkill | Norwegian | 2004-09-03 | 2004-09-02 |  | 0.25 | 902.22 | 902.22
AD 0758 | COLLIERY ROAD | Lackawanna | Dickson City | 2004-12-03 | 2004-11-17 |  | 0 | 5047.18 | 5047.18
AMD 11(2419)101.1 | SOUTH NANTY GLO #1 (WEBSTER) | Cambria | Blacklick | 2004-11-03 | 2004-03-15 |  | 0.1 | 201253 | 201253
AMD 30(4687)101.1 | NEWTOWN (SHANNOPIN) (SW 30610) | Greene | Dunkard | 2004-12-31 | 2003-09-16 |  | 9.6 | 1799201.25 |  | 366201.25 | 1433000
AMD 33(2992)101.1 | CLOVER RUN #1 (BARRETT) | Jefferson | Gaskill | 2004-11-23 | 2004-04-07 |  | 15 | 145721.78 |  |  | 145721.78
AMD 56,65(RES.RECOVERY 2)102.1 | METRO PHASE 2 | Somerset | Elk Lick | 2004-09-20 | 2002-06-05 |  | 0 | 567423.49 |  |  |  |  | 567423.49
AMD 65(1183)202.1 | KEYSTONE | Westmoreland | Derry | 2004-12-09 | 2004-04-05 |  | 3 | 237465.87 |  |  | 237465.87
BD 1892-2 | REOPEN TO BACKFILL CAVE HOLE | Allegheny | Penn Hills | 2004-04-15 | 2004-04-15 |  | 0.1 | 842.91 | 842.91
BD 1963-5 | VROMAN | Clearfield | Morris | 2004-04-12 | 2004-04-07 |  | 0.6 | 1968.36 | 1968.36
BD 1996-3 | HAGERTY | Allegheny | West Mifflin | 2004-05-24 | 2004-05-24 |  | 0.5 | 301.77 | 301.77
BD 2023-5 | BD 2023-5 | Allegheny | Elizabeth | 2004-04-12 | 2004-04-12 |  | 0.2 | 524.33 | 524.33
BD 2080-5 | HUNSICKER | Clearfield | Bradford | 2004-05-18 | 2004-05-18 |  | 0.1 | 464.76 | 464.76
BD 2084-5 | MEOLA (CLEAN) | Cambria | Stonycreek | 2004-05-28 | 2004-05-28 |  | 1 | 545.3 | 545.3
BD 2100 | O'DELL MINE DRAINAGE | Clearfield | Morris | 2004-04-12 | 2004-04-07 |  | 0.1 | 2848.28 | 2848.28
BD 2133-4 | BD 2133-4 | Clearfield | Lawrence | 2004-05-13 | 2004-05-13 |  | 0.5 | 232.43 | 232.43
BD 2168-3 | SHEPLER DRIVE | Allegheny | South Park | 2004-05-12 | 2004-05-12 |  | 0.05 | 1666.93 | 1666.93
BD 2187-8 | WATTERSON | Butler | Buffalo | 2004-04-23 | 2004-04-23 |  | 1.5 | 560.07 | 560.07
BD 2191-4 | ROMANIE | Indiana | Creekside | 2004-04-26 | 2004-04-26 |  | 0.1 | 431.79 | 431.79
BD 2249-5 | WORTON | Allegheny | West Mifflin | 2004-01-09 | 2003-12-29 |  | 0.1 | 2453.08 | 2453.08
BD 2291 | CLEAN PIPES | Allegheny | Penn Hills | 2004-07-21 | 2004-07-21 |  | 0 | 235.7 | 235.7
BD 2291-5 | STECKEL/FELOSO | Allegheny | Penn Hills | 2004-04-14 | 2004-04-14 |  | 0.2 | 487.18 | 487.18
BD 2411 | MONISTARY RUN | Westmoreland | Unity | 2004-07-07 | 2004-07-07 |  | 0 | 290.61 | 290.61
BD 2411-3 | MONESTARY RUN TREATMENT | Westmoreland | Unity | 2004-04-06 | 2004-04-06 |  | 0.1 | 288.75 | 288.75
BD 2415-6 | RENAUD | Clearfield | Lawrence | 2004-05-13 | 2004-05-13 |  | 0.5 | 291.24 | 291.24
BD 2443-2 | PARKER MINE DRAINAGE | Allegheny | Pittsburgh (D) | 2004-04-14 | 2004-04-14 |  | 0.1 | 1238.96 | 1238.96
BD 2475 | MINE DRAINAGE | Clearfield | Morris | 2004-06-29 | 2004-06-22 |  | 0 | 1421.87 | 1421.87
BD 2506-2 | McAFOOSE | Clarion | Redbank | 2004-05-27 | 2004-05-27 |  | 0.4 | 554.16 | 554.16
BD 2507-2 | MINE DRAINAGE | Clearfield | Bradford | 2004-05-18 | 2004-05-18 |  | 0.2 | 203.4 | 203.4
BD 2533 | PIPE CLEANING | Allegheny | Plum | 2004-07-27 | 2004-07-27 |  | 0 | 697.42 | 697.42
BD 2557-1 | WASTE LINE B & T | Cambria | Barr | 2004-05-04 | 2004-05-04 |  | 0 | 534 | 534
BD 2562 | LAUREL FALLS NORTH | Somerset | Summit | 2004-09-13 | 2004-09-13 |  | 0 | 1951.76 | 1951.76
BD 2565-01 | LESCISIN MINE DRAINAGE | Allegheny | Churchill | 2004-08-10 | 2004-08-10 |  | 0.1 | 947.77 | 947.77
BD 2575 | MINE DRAINAGE SYSTME | Fayette | Springhill | 2004-07-02 | 2003-11-03 |  | 0.15 | 3376.29 | 3376.29
BD 2586 | HAULED STONE | Clearfield | Bigler | 2004-07-14 | 2004-07-14 |  | 0 | 597 | 597
BD 2586-1 | YOUHON STRIP MINE | Clearfield | Bigler | 2004-04-20 | 2004-03-22 |  | 0.2 | 57616.01 | 57616.01
BD 2592-1 | PATTON MINE DRAINAGE | Clarion | Highland | 2004-04-19 | 2003-09-09 |  | 0.25 | 8083.97 | 8083.97
BD 2599-1 | BD 2599-1 | Armstrong | Kiskiminetas | 2004-04-21 | 2003-11-25 |  | 4 | 14508.8 | 14508.8
BD 2616-1 | LEYO | Clearfield | Irvona | 2004-05-14 | 2004-04-27 |  | 0.5 | 4349.15 | 4349.15
BD 2619 | PALASCHAK | Allegheny | Monroeville | 2004-09-03 | 2004-07-23 |  | 0.1 | 4807.65 | 4807.65
BD 2620 | LAUREL RUN | Westmoreland | Cook | 2004-05-17 | 2003-10-28 |  | 0.5 | 27520.67 | 27520.67
BD 2623 | MINE DRAINAGE | Beaver | North Sewickley | 2004-06-03 | 2004-06-02 |  | 0.1 | 4231.48 | 4231.48
BD 2628 | BD 2628 | Allegheny | Elizabeth | 2004-01-02 | 2004-01-02 |  | 0.1 | 300.88 | 300.88
BD 2634 | MINE DRAINAGE | Allegheny | Monroeville | 2004-07-09 | 2004-07-08 |  | 0.2 | 2954.59 | 2954.59
BD 2635 | BACKFILLING | Beaver | Darlington | 2004-07-14 | 2004-01-21 |  | 3 | 24333.62 | 24333.62
BD 2636 | MINE DRAINAGE SYSTEM | Allegheny | Penn Hills | 2004-07-30 | 2004-07-21 |  | 0.1 | 5492.69 | 5492.69
BD 2643 | CLEANING CHANNEL | Clinton | West Keating | 2004-08-20 | 2004-08-17 |  | 0.1 | 996.24 | 996.24
BD 2644 | BACKFILLING OF MINE CAVE HOLE | Clarion | Elk | 2004-04-19 | 2004-04-19 |  | 0.1 | 337.26 | 337.26
BD 2645-1 | BD 2645-1 | Elk | Fox | 2004-05-07 | 2004-05-07 |  | 0.3 | 967.73 | 967.73
BD 2647-1 | BD 2647-1 | Somerset | Shade | 2004-05-22 | 2004-05-22 |  | 0.5 | 784.7 |  | 784.7
BD 2647-2 | BD 2647-2 | Somerset | Shade | 2004-05-22 | 2004-05-22 |  | 0.5 | 748.69 | 748.69
BD 2648-1 | MARTIN | Clearfield | Decatur | 2004-03-22 | 2004-03-22 |  | 0.1 | 980.67 | 980.67
BD 2649 | MINE DRAINAGE SYSTEM | Allegheny | Penn Hills | 2004-07-01 | 2004-01-14 |  | 0.1 | 6853.04 | 6853.04
BD 2650 | MINE DRAINAGE SYSTEM | Allegheny | Penn Hills | 2004-06-23 | 2004-06-08 |  | 0.2 | 8006.71 | 8006.71
BD 2652 | MINE DRAINAGE SYSTEM | Allegheny | West Mifflin | 2004-08-24 | 2004-08-18 |  | 0.2 | 3006.27 | 3006.27
BD 2654 | WELL CAPS | Cambria | Barr | 2004-04-15 | 2004-04-15 |  | 0 | 426.63 | 426.63
BD 2655-1 | PIPE DELIVERY MATERIALS PART. | Fayette | Springhill | 2004-05-21 | 2004-05-20 |  | 0.1 | 1597.5 | 1597.5
BD 2656 | MINE DRAINAGE | Clearfield | Beccaria | 2004-08-26 | 2004-05-25 |  | 0.1 | 7166.74 | 7166.74
BD 2657 | MINE DRAINAGE SYSTEM | Allegheny | Penn Hills | 2004-08-09 | 2004-07-29 |  | 0.1 | 5403.76 | 5403.76
BD 2658-1 | KANOUFF | Clearfield | Morris | 2004-04-13 | 2004-04-13 |  | 0.2 | 464.94 | 464.94
BD 2659 | TOBY CREEK DELIVERY | Elk | Fox | 2004-08-20 | 2004-07-06 |  | 0 | 1891.75 | 1891.75
BD 2659-01 | WASTE LIME FOR AMD - TOBY | Elk | Fox | 2004-05-07 | 2004-05-07 |  | 0.1 | 417.45 | 417.45
BD 2659-02 | WASTE LIME FOR AMD - TOBY | Elk | Fox | 2004-06-18 | 2004-06-18 |  | 0.1 | 864.11 |  | 864.11
BD 2661 | NUMBER 9 MINE | Cambria | Northern Cambria | 2004-07-29 | 2004-06-22 |  | 0 | 1642.69 | 1642.69
BD 2663 | LITTLE MILL CREEK (MARKLE & HANLON) | Clarion | Millcreek | 2004-08-13 | 2004-08-09 |  | 0 | 6540.83 |  | 6540.83
BD 2664 | MINE DRAINAGE | Greene | Monongahela | 2004-08-11 | 2004-08-11 |  | 0 | 510.86 | 510.86
BD 2666-2 | AME ZION CHURCH MINE DRAINAGE (GA) | Allegheny | Pittsburgh (D) | 2004-12-31 | 2004-12-20 |  | 0 | 11675.34 | 11675.34
BD 2666-3 | AME ZION CHURCH MINE DRAINAGE (GA) | Allegheny | Pittsburgh (D) | 2004-12-31 | 2004-12-20 |  | 0 | 20226.31 | 20226.31
BD 2667 | CAVE HOLES | Westmoreland | Derry | 2004-08-04 | 2004-08-04 |  | 0.1 | 1064.84 | 1064.84
BD 2669 | MINE DRAINAGE | Allegheny | Monroeville | 2004-09-01 | 2004-08-25 |  | 0.1 | 7377.17 | 7377.17
BD 2670 | CAVE HOLES | Butler | Center | 2004-08-06 | 2004-08-05 |  | 0.1 | 1188.96 | 1188.96
BD 2674 | SUBSIDENCE | Washington | Cecil | 2004-09-07 | 2004-09-07 |  | 0 | 465.18 | 465.18
BD 2678 | MINE DRAINAGE | Allegheny | Forest Hills | 2004-07-28 | 2004-07-28 |  | 0.1 | 2024.7 | 2024.7
BD 2679 | WEST MIFFLIN | Allegheny | West Mifflin | 2004-09-02 | 2004-09-01 |  | 0.1 | 1531.42 | 1531.42
BD 2684 | BF 506 CLEANING | Clarion | Porter | 2004-08-11 | 2004-08-11 |  | 0.1 | 938.77 | [6 empty] | 938.77
BD 2685 | WEAVER DITCH | Clarion | Richland | 2004-08-16 | 2004-08-16 |  | 0.1 | 295.92 | [6 empty] | 295.92
BD 2686 | BOG | Clarion | Porter | 2004-08-12 | 2004-08-12 |  | 0 | 494.39 | [6 empty] | 494.39
BD 2687 | KNOX OFFICE DITCH | Clarion | Monroe | 2004-08-16 | 2004-08-16 |  | 0.1 | 468.4 | [6 empty] | 468.4
BD 2688 | MINE SUBSIDENCE | Clarion | Elk | 2004-08-16 | 2004-08-16 |  | 0.1 | 328.8 | 328.8
BF 275-102.1 | GLENN COAL CO. | Jefferson | Beaver | 2004-06-30 | 2003-01-01 |  | 42 | 215564.51 | [5 empty] | 78242 |  | 137322.51
BF 300-102.1 | BENJAMIN COAL CO | Clearfield | New Washington | 2004-05-19 | 2004-04-06 |  | 50 | 62225 | [6 empty] | 62225
BF 328-102.1 | JOHNSON & MORGAN | Centre | Snow Shoe | 2004-05-19 | 2004-04-06 |  | 43.4 | 23230 | [6 empty] | 23230
BF 329-102.1 | BENJAMIN COAL CO | Clearfield | Bell | 2004-05-19 | 2004-04-06 |  | 70 | 134084.01 | [6 empty] | 134084.01
BF 358-102.1 | HARMON COAL CO | Jefferson | Ringgold | 2004-05-19 | 2004-04-06 |  | 301 | 1972.5 | [6 empty] | 1972.5
BF 361-102.1 | LAWRENCE RESOURCES | Clearfield | Newburg | 2004-05-19 | 2004-04-06 |  | 11.6 | 32114.59 | [5 empty] | 32114.59
BF 367-102.1 | BILL TURNER ENTERPRISES | Armstrong | Boggs | 2004-05-19 | 2004-04-06 |  | 7.5 | 8725 | [6 empty] | 8725
BF 369-102.1 | H & D COAL COMPANY(NEMSER) | Butler | Marion | 2004-05-19 | 2004-04-06 |  | 3 | 2050 | [5 empty] | 2050
BF 376-102.1 | GLENDALE CONTRACTING CO. | Clearfield | Beccaria | 2004-05-19 | 2004-04-06 |  | 25 | 16283.75 | [5 empty] | 8748.2 | 7535.55
BF 377-102.1 | EASTERN ENERGY CORPORATION | Clearfield | Lawrence | 2004-05-19 | 2004-04-06 |  | 6 | 6017.5 | [6 empty] | 6017.5
BF 424-101.1 | BENJAMIN COAL CO. | Clearfield | Bell | 2004-07-02 | 2002-11-22 |  | 19.5 | 196983.04 | [5 empty] | 120702.54 | 76280.5
BF 448-101.1 | COAL PROCESSING, INC. (I) | Westmoreland | Mount Pleasant | 2004-10-14 | 2003-05-09 |  | 14.7 | 196837.76 | 191836.76 |  |  |  |  | 5000 |  | 1
BF 463-101.1 | AVERY COAL CO., INC. | Clearfield | Chest | 2004-09-09 | 2004-04-15 |  | 10.5 | 50302.5 | [5 empty] | 24840 |  | 25462.5
BF 474-101.1 | E & J CONTRACTING CO. | Fayette | Dunbar | 2004-09-15 | 2003-05-01 |  | 62.2 | 436490 | [5 empty] | 66927.5 | 161055 | 208507.5
BF 484-102.1 | BRYAR CONSTRUCTION | Westmoreland | Hempfield | 2004-10-14 | 2004-04-19 |  | 26.2 | 155604.75 | [5 empty] | 23100 |  | 132504.75
DGS 181-14.1 | AUBURN DAM | Schuylkill |  | 2004-04-29 | 2002-10-15 |  | 0 | 38653.15 | [7 empty] | 38653.15
DMF 003-102.1 | CANNEL COAL COMPANY | Armstrong | Mahoning | 2004-05-19 | 2004-04-06 |  | 9 | 8990 | [6 empty] | 8990
OSM 02(1706)101.1 | HIGHLAND AVENUE | Allegheny | Swissvale | 2004-05-18 | 2004-02-12 |  | 1.25 | 62793.23 | 62793.23
OSM 04(6293)101.1 | COUNTY SCHOOL EAST | Beaver | Big Beaver | 2004-05-20 | 2001-05-30 |  | 79 | 858125.52 | 132456.52 | [6 empty] | 725669
OSM 10(3760)102.1 | ANNANDALE S.W. II | Butler | Cherry | 2004-06-10 | 2003-05-27 |  | 38.15 | 737526.23 | 737525.23 | [6 empty] | 1
OSM 11(3576)101.1 | BRUBAKER RUN | Cambria | Elder | 2004-06-30 | 2003-05-28 |  | 13.7 | 169301.29 | 169301.29
OSM 16(6220)101.1 | STEP CREEK | Clarion | Paint | 2004-11-09 | 2004-07-16 |  | 3.6 | 27577 | 27577
OSM 17(4579)102.1 | PLEASANT HILL WEST #2 | Clearfield | Decatur | 2004-08-04 | 2004-05-06 |  | 0.5 | 57035 | 57035
OSM 17(6888)101.1 | LITTLE ANDERSON CREEK | Clearfield | Brady | 2004-08-13 | 2003-02-25 |  | 5.9 | 43717.52 | 21217.52 | [6 empty] | 22500
OSM 17(7004)101.1 | OWENS CEMETERY | Clearfield | Lawrence | 2004-08-04 | 2004-05-11 |  | 1.5 | 67780 | 67780
OSM 24(3895)101.1 | WINSLOW HILL III | Elk | Benezette | 2004-10-20 | 2003-07-11 |  | 28.8 | 391296.68 | 391296.68
OSM 35(1748)101.1 | RIVERSIDE EAST | Lackawanna | Jessup | 2004-12-16 | 2004-12-03 |  | 0.2 | 17113.33 | 17113.33
OSM 35(3738)101.1 | NORTH GOLF COURSE | Lackawanna | Taylor | 2004-07-19 | 2004-02-12 |  | 5.9 | 50465.5 | 50465.5
OSM 35(3743)101.1 | O'CONNER RESERVOIR (JESSUP BORO) | Lackawanna | Jessup | 2004-04-27 | 2002-02-22 |  | 113.9 | 3907596.03 | [5 empty] | 1132900.03 |  | 2774696
OSM 35(3743)102.1 | O'CONNER RESERVOIR (JESSUP BORO) | Lackawanna | Jessup | 2004-08-03 | 2003-10-23 |  | 41.9 | 332763.06 | 43477.05 | [6 empty] | 289286
OSM 40(1565)101.1 | PLAINSVILLE FLOODPLAIN | Luzerne | Plains | 2004-04-19 | 2003-10-29 |  | 0.5 | 156288 | 156288
OSM 54(3652)101.1 | NEWTOWN WEST | Schuylkill | Reilly | 2004-11-08 | 2003-12-03 |  | 47.6 | 405659.5 |  |  |  | 405659.5
OSM 56(2520)205.1 | NORTH CENTRAL CITY | Somerset | Shade | 2004-05-13 | 2003-09-16 |  | 0.32 | 18947.5 | 18947.5
2004 Completions: |  | 123 | Projects |  |  |  | 1139.02 | 12164655.58 | 2659453.23 | 374390.89 | 1816187.65 | 405659.5 | 567423.49 | 1494624.86 | 492312.54 | 4354603.41
Projects Completed Year-to-date, Calendar Year 2005
AD 0754 | LARKSVILLE SOUTHWEST | Luzerne |  | 2005-06-21 | 2004-12-08 |  | 0 | 69297.92 | 69297.92
AMD 03(0743)102.1 | NUMINE (WHITE LAKE) | Armstrong | Cowanshannock | 2005-06-03 | 2005-02-11 |  | 2.8 | 31488 |  |  | 31488
BF 091-101.1 | GLOSEK BROTHERS COAL CO. | Northumberland | West Cameron | 2005-05-10 | 2004-05-07 |  | 41 | 393782.12 | [5 empty] | 5000 |  | 388782.12
BF 302-105.1 | REM COAL CO. | Jefferson | Union | 2005-10-31 | 2003-04-08 |  | 2 | 233986.49 | [5 empty] | 233986.49
BF 372-101.1 | GLENN COAL CO. (ACT 181) | Jefferson | McCalmont | 2005-05-27 | 2003-10-22 |  | 48.8 | 290998 | 246797 |  |  |  |  | 44201
BF 467-101.1 | PENGROVE COAL COMPANY(BEAN) | Butler | Cherry Valley | 2005-07-07 | 2004-10-05 |  | 2 | 106608.95 | [5 empty] | 106608.95
BF 488-101.1 | McGAL COAL | Allegheny | Forward | 2005-05-06 | 2004-10-05 |  | 4 | 114010.6 | 110572.6 |  |  |  |  | 3438
BF 511-101.1 | LAURA D COAL, INC. | Somerset | Jenner | 2005-07-29 | 2004-10-26 |  | 4.3 | 23600 | [5 empty] | 22320 | 1280
CRF 006-101.1 | WHITE ROCK FUEL CO. | Fayette | Georges | 2005-01-19 | 2003-12-09 |  | 22 | 78435.42 | [5 empty] | 21758.52 | 56676.9
OSM 02(1496)101.1 | WEST STARZ WATERLINE (PASS THRU) | Allegheny | West Deer | 2005-06-09 | 2004-07-01 |  | 0 | 28945.17 | 28945.17
OSM 10(6375)101.1 | DEEGAN WEST | Butler | Marion | 2005-05-09 | 2003-12-18 |  | 18.1 | 190270.1 | 190270.1
OSM 11(BARNES-WATKINS)102.1 | BARNES-WATKINS REF. PILE REMED.(SW 30438 | Cambria | Barr | 2005-05-31 | 2004-03-12 |  | 4.5 | 1214875 | 1124875 | [6 empty] | 90000
OSM 14(4556)101.1 | CASANOVA | Centre | Rush | 2005-04-25 | 2004-02-05 |  | 8.1 | 43943.2 | 43943.2
OSM 17(4454)101.1 | BCI WATERLINE (GA) | Clearfield | Beccaria | 2005-05-24 | 2005-04-01 |  | 0 | 31918.87 | 31918.87
OSM 19(4034,2000,1688) | CENTRALIA MERCURY MONITORING | Columbia | Centralia | 2005-04-14 | 2004-12-01 |  | 0 | 112260 | 112260
OSM 24(2211)102.1 | RIDGWAY HILL | Elk | Ridgway | 2005-05-20 | 2004-09-30 |  | 7 | 122449 | 122449
OSM 26(0151)202.1 | DUNBAR TWP. | Fayette | Dunbar | 2005-10-06 | 2004-09-03 |  | 3 | 79729.9 | 79729.9
OSM 30(2766)101.1 | CRUCIBLE NORTH | Greene | Cumberland | 2005-04-26 | 2004-05-28 |  | 8 | 216057.62 | 201057.62 | [5 empty] | 15000
OSM 32(2444)101.1 | CALVERY CHURCH | Indiana | Green | 2005-07-01 | 2005-03-07 |  | 4.9 | 45308.93 | 45308.93
OSM 35(2090)101.1 | JESSUP CEMETERIES | Lackawanna | Jessup | 2005-01-12 | 2002-06-20 |  | 70.3 | 1504773.36 | 12740.5 |  |  | 1492032.86
OSM 37(0185)101.1 | FRIDAYS HILL ROAD | Lawrence | Wayne | 2005-05-19 | 2004-03-04 |  | 10 | 64007.5 | 64007.5
OSM 40(2128)101.1 | WARRIOR GAP | Luzerne | Warrior Run | 2005-06-06 | 2004-09-27 |  | 19.9 | 260900 | 260900
OSM 40(2239,3035)101.1 | NEW BOSTON ROAD 2 NORTH, OLD BOSTON | Luzerne | Jenkins | 2005-11-16 | 2005-06-06 |  | 35 | 341051.88 | 341051.88
OSM 49(2067)101.1 | GOWEN CITY NORTHWEST | Northumberland | Coal | 2005-05-24 | 2004-03-05 |  | 20.5 | 271638.87 | 271638.87
OSM 54(TREMONT II)101.1 | TREMONT II - CONSTRUCTION (NE 30437) | Schuylkill | Tremont | 2005-09-30 | 2004-03-04 |  | 0 | 174309.62 | 158309.62 | [6 empty] | 16000
OSM 56(0240)101.1 | CENTRAL CITY | Somerset | Shade | 2005-01-05 | 2004-09-03 |  | 0.1 | 120983 | 120983
OSM 56(0775)102.1 | LISTIE SOUTH | Somerset | Somerset | 2005-05-19 | 2004-03-24 |  | 14 | 250110 | 250110
OSM 63(1441)101.1 | MCDONALD SOUTH | Washington | McDonald | 2005-06-15 | 2005-04-18 |  | 6 | 402502.75 | 402502.75
2005 Completions: |  | 28 | Projects |  |  |  | 356.3 | 6818242.27 | 4289669.43 | 0 | 31488 | 1492032.86 | 0 | 437312.96 | 72956.9 | 494782.12
Active Projects, Under Construction, Future Completion Date
AMD 08(3998)101.2 | COAL RUN AMD REMEDIATION (GA) | Bradford | Franklin | 2006-12-31 | 2005-04-20 |  | 0 | 23270 |  |  | 23270
AMD 11(2707)101.2 | JOHNSTOWN REDEVELOPMENT (GA) CD040137 | Cambria | Stonycreek | 2006-12-31 | 2005-04-01 |  | 0 | 37114 |  |  | 37114
AMD 11(4090)101.1 | DUMAN LAKE PARK (BARNES AND TUCKER) (GA) | Cambria | Blacklick |  | 2004-09-17 |  | 0 | 970120.98 | 970120.98
AMD 14(6816)101.1 | PINE GLEN EAST | Centre | Burnside | 2006-05-16 | 2004-05-06 |  | 0 | 819767 |  | 714948.35 |  |  |  | 158062.8
AMD 16(1061)101.1 | LC20D PASSIVE MINE DRAINAGE (GA) | Clarion | Farmington | 2006-12-31 | 2005-03-23 |  | 10 | 351734 |  |  | 351734
AMD 26(0429)103.1 | MELCROFT (GA) | Fayette | Saltlick | 2006-06-30 | 2004-06-30 |  | 0 | 325000 |  |  | 325000
AMD 26(2767)102.1 | ROMNEY NORTH (KALP DISCHARGE)(GA) | Fayette | Saltlick | 2006-12-31 | 2005-04-20 |  | 10 | 1661407 |  | 1661407
AMD 32(2404)101.1 | TIDE MINE POOL TREATMENT (GA) | Indiana | Center | 2005-05-01 | 2004-05-13 |  | 50 | 394773.5 |  |  | 394773.5
AMD 42(0421)101.1 | TWO MILE RUN (PASS THROUGH AGREEMENT) | McKean | Sergeant | 2005-12-31 | 2003-09-18 |  | 5 | 53575 |  |  | 53575
AMD 56(1488)102.1 | JENNER PASSIVE TREATMENT SYSTEM (GA)CD040227 | Somerset | Jenner | 2006-12-31 | 2005-05-03 | 2005-02-01 | 0 | 106682 |  |  | 106682
AMD 56(3077)202.1 | HOFFMAN ZION CHURCH (HOFFMAN RUN) | Somerset | Jenner | 2005-10-27 | 2004-09-14 |  | 0 | 412194.22 | 406492.22
AMD 56,65(RES.RECOVERY 3)103.1 | METRO PHASE 3 | Somerset | Elk Lick | 2005-03-31 | 2003-09-26 |  | 0 | 500000 |  |  |  |  | 500000
AMD 59(1891,6657)101.1 | ARNOT SAP-ALD (GA) | Tioga | Bloss | 2006-12-31 | 2004-11-04 |  | 0 | 102603 |  |  | 1 |  |  |  |  | 102603
BF 378-101.1 | HILL COAL CO. ENTERPRISES (I) (ACT 181) | Clearfield | Boggs | 2007-02-12 | 2005-02-15 |  | 37 | 425310 | 390310 |  |  |  |  | 35000
BF 438-102.1 | AVERY COAL CO., INC. | Clinton | Beech Creek | 2005-10-31 | 2003-05-19 |  | 12 | 1348522 | [5 empty] | 278435.79 |  | 1070086.21
BF 440-201.1 | ATTILIO CICCONI | Fayette | Luzerne | 2006-01-12 | 2004-11-08 |  | 54 | 992000 | [5 empty] | 36000 | 204400.03 | 751599.97
BF 442-101.1 | T & T CLAY COMPANY | Clearfield | Boggs | 2006-02-27 | 2005-04-28 |  | 12 | 103110 | [5 empty] | 21220.09 | 81889.91
BF 469-201.1 | ROBERT F. TAYLOR & BRYAN NORTHWEST | Armstrong | Wayne | 2007-01-11 | 2005-06-29 |  | 79 | 992023 | 674575.64 |  |  |  |  | 150590 | 166857.36
BF 472-101.1 | CT & LT ENTERPRISES, INC. | Greene | Jefferson | 2005-07-23 | 2003-07-31 |  | 23.8 | 130155 | [5 empty] | 77851.25 | 52303.75
BF 485-101.1 | ELIZABETHVILLE NORTH (AD COAL COMPANY) | Dauphin | Washington | 2005-09-07 | 2004-09-15 |  | 4.5 | 184510 | 104241 |  |  |  |  | 1869.6 | 78399.4
BF 490-101.1 | GRAHAM BROS. LUMBER CO., INC. | Clearfield | Boggs | 2006-02-21 | 2004-01-22 |  | 0 | 421578.4 | [5 empty] | 188818.47 | 232759.93
BF 493-101.1 | THOMPSON BROTHERS COAL CO. | Clearfield | Morris | 2006-01-20 | 2005-05-12 |  | 54.5 | 293375.5 | [5 empty] | 293375.5
BF 504-101.1 | ROYAL RECLAMATION, INC. | Westmoreland | Mount Pleasant | 2005-10-27 | 2005-04-06 |  | 8.2 | 48719.13 | [5 empty] | 2175 | 46544.13
BF 505-101.1 | CHARLES BIZICH | Westmoreland | Bell |  | 2004-12-01 |  | 4 | 32050 | [5 empty] | 4008.07
DMF 010-102.1 | SKY HIGH COAL COMPANY | Schuylkill | Porter | 2006-01-31 | 2005-06-07 |  | 3 | 53423 | [5 empty] | 3230 | 50193
DMF 011-101.1 | MEADOWS AND LEONARD MINING, INC. | Cambria | Adams | 2007-03-05 | 2004-03-08 |  | 19.5 | 186983 | [5 empty] | 186983
NCF 005-101.1 | McCORMICK MATERIALS | Erie | Le Boeuf |  | 1998-01-05 |  | 6 | 0 | [5 empty] | 11600
OSM 02(0796)101.1 | WEST SMITHFIELD ROAD | Allegheny | Lincoln | 2006-05-15 | 2004-10-14 |  | 16 | 223621.5 | 223621.5
OSM 02(3813)101.1 | RED HOT / CHRISTY ROAD | Allegheny | West Deer |  | 2005-10-12 |  | 0 | 34225 | 34225
OSM 03(3902)101.1 | CRAIGSVILLE SOUTHWEST | Armstrong | West Franklin | 2006-05-02 | 2005-03-04 |  | 54.8 | 919328.7 | 919328.7
OSM 04(0153)101.1 | JORDAN RUN | Beaver | Big Beaver | 2006-04-05 | 2005-07-01 |  | 24 | 367419 | 367419
OSM 04(1259)101.1 | FALLSTON | Beaver | Fallston |  | 2005-10-05 |  | 2 | 58900 | 58900
OSM 04(1261)101.1 | FREEDOM | Beaver | New Sewickley | 2005-08-29 | 2005-05-24 |  | 3 | 59089.55 | 59089.55
OSM 10(3760)103.1 | ANNANDALE S.W. III | Butler | Cherry |  | 2005-10-20 |  | 84.1 | 1489767 | 1489767
OSM 10(4506)101.1 | WEST LIBERTY SOUTH WEST | Butler | West Liberty | 2006-06-14 | 2005-07-19 |  | 18 | 288328 | 288328
OSM 11(0826)102.1 | SPANGLER ATHLETIC FIELD | Cambria | Northern Cambria |  | 2005-11-15 |  | 2 | 131631.4 | 131631.4
OSM 11(1018)101.1 | HOLLENTOWN NORTHEAST | Cambria | Reade | 2006-05-02 | 2005-03-04 |  | 39.6 | 548319 | 548319
OSM 11(BARNES-WATKINS)103.1 | BARNES-WATKINS PHASE2 (GA) CB040457 | Cambria | Barr | 2006-12-31 | 2005-04-11 |  | 13.5 | 3188958 | 3188958
OSM 13(4066)102.1 | LANSFORD NORTH 2 | Carbon | Lansford | 2006-03-05 | 2003-10-23 |  | 105 | 2459044.45 | 2196715.9 |  |  | 262328.55
OSM 13(4652)101.1 | LANSFORD EAST | Carbon | Lansford | 2005-12-20 | 2004-12-23 |  | 11.5 | 282284 | 282284
OSM 13,40(4966,4121)101.1 | BUCK MOUNTAIN & OWL HOLE | Carbon | Lausanne |  | 2005-10-12 |  | 1 | 30000 | 30000
OSM 16(0065)101.1 | FAIRHILL COAL | Clarion | Redbank |  | 2005-11-08 |  | 10.25 | 106142 | 106142
OSM 16(6045)101.1 | FROGTOWN NORTHEAST (LIMESTONE TOWNSHIP WATERLINE (GA) | Clarion | Limestone | 2007-12-31 | 2005-07-07 |  | 0 | 1134064 | 1134064
OSM 17(0084)103.1 | NEEDFUL WEST | Clearfield | Bradford | 2006-02-03 | 2005-06-23 |  | 0 | 359900 | 359900
OSM 17(6955)101.1 | BARK CAMP COMPLEX (GA) | Clearfield | Huston |  | 2005-01-18 |  | 2.5 | 333333 | 333333
OSM 17(7103)101.1 | OHIO SCHOOL (CONSULT. DESIGN) | Clearfield | Decatur | 2005-06-15 | 2004-04-28 |  | 74 | 373471.3 | 373471.3
OSM 17(7158)101.1 | SHAWVILLE NORTH | Clearfield | Goshen | 2006-06-22 | 2005-06-23 |  | 0 | 681767 | 681767
OSM 17(7163)102.1 | McDOWELL MOUNTAIN SOUTH | Clearfield | Bradford | 2006-02-21 | 2005-07-12 |  | 0 | 192000 | 192000
OSM 24(3894)101.1 | WINSLOW HILL II | Elk | Benezette | 2005-09-11 | 2005-01-28 |  | 14.5 | 565635.56 | 565635.56
OSM 24(BRANDY CAMP)101.1 | BRANDY CAMP/BLUE VALLEY (NW 30032) | Elk | Horton | 2006-06-30 | 2004-01-08 |  | 2 | 200000 |  |  | 182000 |  |  |  |  | 18000
OSM 24(DENTS RUN)101.1 | DENTS RUN-WINSLOW HILL 3 (CORPS OF ENG.) | Elk | Benezette | 2008-06-30 | 2004-12-03 |  | 0 | 3028000 | 2818000 | [6 empty] | 210000
OSM 26(2718)103.1 | PERCY MINE FIRE | Fayette | North Union | 2007-06-22 | 2005-04-21 |  | 200 | 3203000 | 3203000
OSM 26(4733)101.1 | GANS NORTHWEST | Fayette | Springhill | 2006-05-15 | 2005-02-15 |  | 12.2 | 88612.1 | 88353.75
OSM 30(2791-MATHER)101.1 | MATHER PILE RECLAMATION (SW 30649) | Greene | Morgan | 2005-12-31 | 2004-04-28 |  | 77 | 2971394 | 2832394 | [6 empty] | 139000
OSM 31(6026)101.1 | LUCIANA BOTTOMS WEST | Huntingdon | Todd | 2006-02-10 | 2004-05-28 |  | 90 | 1284767 | 1284767
OSM 32(2722)101.1 | WEHRUM NORTHEAST | Indiana | Buffington | 2006-12-31 | 2005-06-10 |  | 0 | 46180 | 46180
OSM 32(3327)101.1 | GLEN CAMPBELL NORTH | Indiana | Banks | 2005-09-09 | 2004-12-29 |  | 20 | 256182.4 | 256182.4
OSM 35(1519,2087,2088)201.1 | FALL RUN, S.W. & CARBONDALE N.E. | Lackawanna | Carbondale | 2008-05-08 | 2005-09-06 | 2005-06-30 | 226 | 5413233 | 5413233
OSM 35(LEES CREEK)101.1 | LEES CREEK STREAM REHAB. (NE 30268) | Lackawanna | Carbondale | 2005-06-30 | 2004-01-08 |  | 0 | 52607 |  |  | 47607 |  |  |  |  | 5000
OSM 37(S.WELLS McCREADY)101.1 | S. WELLS McCREADY (NW 30569) - PHASE III | Lawrence | New Beaver | 2006-06-30 | 2004-01-29 |  | 14 | 156146 | 148146 | [6 empty] | 8000
OSM 40(2138)102.1 | CURRYHILL-AVONDALE | Luzerne | Plymouth | 2007-10-12 | 2004-03-24 |  | 136.8 | 3954100.28 | 3954100.28
OSM 40(3213)201.1 | CRANBERRY RIDGE | Luzerne | Hazleton | 2007-01-12 | 2004-02-06 |  | 140 | 2755797.3 |  |  |  | 2755797.3
OSM 40(CAN DO)101.1 | CAN DO, INC. INNOVATION (NE 30299) | Luzerne | Hazle | 2005-06-30 | 2004-04-19 |  | 0 | 444615 | 402516 | [6 empty] | 42099
OSM 49(COAL TWP)101.1 | KULPMONT SOUTHWEST (COAL TWP) | Northumberland | Coal |  | 2004-08-04 |  | 0 | 1173926 | 1173927
OSM 54(2024)101.1 | SHARP MOUNTAIN PHASE III (GA) | Schuylkill | Pottsville | 2006-12-31 | 2005-04-01 |  | 0 | 500000 | 500000
OSM 54(3634)102.1 | MOUNT PLEASANT SOUTH | Schuylkill | Foster | 2005-05-23 | 2004-03-24 |  | 51.6 | 639526 | 639526
OSM 54(4064)101.1 | PISGAH RIDGE WEST | Schuylkill | Tamaqua | 2005-09-08 | 2002-09-11 |  | 105.3 | 3049740.46 | 37684.75 |  |  | 3012055.71
OSM 56(BOSWELL)101.1 | BOSWELL 2 AMD TREATMENT (SW 30167) | Somerset | Jenner | 2006-06-30 | 2004-01-29 |  | 78 | 258595 | 193595 | [6 empty] | 65000
OSM 63(0046)101.1 | CHARTIERS | Washington | Chartiers | 2007-03-12 | 2004-09-14 |  | 0 | 3393210.8 | 3393210.8
OSM 63(3803)201.1 | MONONGAHELA SOUTH NO. 1 (CONSULT.DESIGN) | Washington | Monongahela | 2005-06-30 | 2003-10-07 |  | 0 | 1474083.7 | 1474083.7
OSM 64,35(YUCCA FLATS)101.1 | LACKAWANNA RIVER/YUCCA FLATS (NE 30634) | Lackawanna | Clifton | 2005-06-30 | 2004-03-15 |  | 0 | 21000 |  |  | 17000 |  |  |  |  | 4000
Future Completions: |  | 71 | Contracts |  |  |  | 2021.15 | 59161944.23 | 43969539.43 | 2376355.35 | 1538756.5 | 6030181.56 | 500000 | 1449219.57 | 913347.51 | 2415388.18
Active Design Projects, Future Contract Award Date
AD 0367 | MARY D OPENINGS | Schuylkill | Schuylkill |  |  |  | 0.6
AD 0673 | FALLS CREEK | Bradford | Franklin |  |  |  | 0.2
AD 0675 | HECKSCHERVILLE | Schuylkill | Cass |  |  |  | 0.1
AD 0706 | AD 0706 | Luzerne | Hanover |  |  |  | 0.25
AD 0729 | COLLIERY ROAD | Lackawanna | Dickson City |  |  |  | 0.1
AD 0735 | MAHANOY MOUNTAIN | Northumberland | Zerbe |  |  |  | 0.2
AD 0755 | SWOYERSVILLE NORTH | Luzerne |  |  |  |  | 0
AD 0756 | COURTDALE | Luzerne |  |  |  |  | 0
AD 0759 | DOOLEYVILLE | Northumberland |  |  |  |  | 0
AD 0762 | TAYLOR MAIN AND SUPPLY SHAFTS | Lackawanna | Taylor |  |  |  | 0
AD INQ 04-11-362 | PIKE STREET MINE TUNNEL | Lackawanna | Carbondale |  |  |  | 0
AD INQ 05-01-014 | SOMMERS WATER PROBLEM | Schuylkill | Palo Alto |  |  |  | 0
AD INQ 05-01-021 | ZUCHINSKI SUBSIDENCE | Lackawanna | Old Forge |  |  |  | 0
AD PA 1333 | BUTLER | Luzerne | Pittston |  |  |  | 0
AD PA 1610 | NO. 11 VEIN | Northumberland | Coal |  |  |  | 0
AD PA 1782 | TEAGLE | Lackawanna | Scranton |  |  |  | 0.4
AD PA 2004 | AD PA 2004 | Dauphin | Williams |  |  |  | 0.25
AD PA 2152 | STEARNS COLLIERY | Luzerne | Newport |  |  |  | 0
AD PA 2164 | BLACK DESERT | Luzerne | Exeter |  |  |  | 0
AMD 02(0488)102.1 | WINGFIELD PINES (GD050201) | Allegheny | Bridgeville |  |  | 2005-11-01 | 0
AMD 10(6594)101.1 | DESALE NORTH AMD ABATEMENT PROJECT | Butler | Venango |  |  |  | 65
AMD 11(0632)101.1 | SALTLICK RUN (MINERAL POINT) | Cambria | Jackson |  |  |  | 3
AMD 11(1110)101.1 | BRUBAKER RUN | Cambria | Dean |  |  |  | 0
AMD 11(2707)101.1 | SOLOMON RUN | Cambria | Stonycreek |  |  |  | 0
AMD 11(2711)102.1 | JANDY (CD050369) | Cambria | Richland |  |  | 2005-11-01 | 0
AMD 18(0817)101.1 | FRAN CONTRACTING | Clinton | East Keating |  |  | 2006-06-27 | 16
AMD 18(1122)101.1 | ROBBINS HOLLOW | Clinton | Leidy |  |  |  | 0
AMD 24(6134)102.1 | BRANDY CAMP S. (LITTLE TOBY) | Elk | Fox
AMD 24(6134)103.1 | BRANDY CAMP (KD050010) | Elk | Fox |  |  | 2005-11-01 | 0
AMD 26(0429)102.1 | MELCROFT PHASE 2 | Fayette | Saltlick |  |  |  | 30
AMD 26(0429)104.1 | MELCROFT MINE POOL LOWERING | Fayette | Saltlick |  |  | 2005-10-15 | 0
AMD 31(6959)102.1 | JOLLER (CD050205) | Huntingdon | Todd |  |  | 2005-11-01 | 0
AMD 32(2404)102.1 | YC2C TREATMENT SYSTEM REHAB. - JUDY 14 | Indiana | Center |  |  | 2005-11-01 | 0
AMD 32(2467)101.1 | WEHRUM DISCHARGE | Indiana | Buffington |  |  |  | 0
AMD 33(1147)101.1 | SUGAR CAMP RUN DISCHARGES (KD050285) | Jefferson | Winslow |  |  | 2005-11-01 | 0
AMD 42(0420)101.1 | GUM BOOT RUN | McKean | Sergeant |  |  |  | 9
AMD 65(2971)101.1 | PINE RUN | Westmoreland | Allegheny |  |  |  | 30
AMD 65(3783)101.1 | HOOVERVILLE SOUTH (NINEVAH) | Westmoreland |  |  |  |  | 550
BD 04-06-387 | BONE MINE DRAINAGE | Allegheny | Wilkins |  |  |  | 0.2
BD 04-09-565 | CRAWFORD MINE DRAINAGE | Allegheny | Penn Hills |  |  |  | 0.2
BD 1744 | CASSIDY | Westmoreland | Irwin |  |  |  | 1
BD 1867-4 | KIM | Lawrence | Neshannock |  |  |  | 0.5
BD 1967 | FRANK | Allegheny | Mount Oliver |  |  |  | 0.5
BD 2012 | DRAVOSBURG | Allegheny | Dravosburg |  |  |  | 0.2
BD 2056 | SCHRADER CREEK | Bradford |  |  |  |  | 0.5
BD 2057 | SCHRADER CREEK | Bradford |  |  |  |  | 0.5
BD 2058 | SCHRADER CREEK | Bradford |  |  |  |  | 0.5
BD 2061 | SCHRADER CREEK | Bradford | Franklin |  |  |  | 0.5
BD 2063 | MANN | Allegheny | South Park |  |  |  | 1
BD 2119-2 | CORDEK | Cambria | South Fork |  |  |  | 0.1
BD 2291-6 | STECKEL/FELOSO | Allegheny | Penn Hills |  |  |  | 0.2
BD 2315-3 | PALLADINO | Allegheny | Plum |  |  |  | 0.2
BD 2429 | HOLLIS | Centre | Rush |  |  |  | 0.2
BD 2449 | HINDS | Mercer | Pine |  |  |  | 0.2
BD 2457-1 | MINE DRAINAGE | Clearfield | Clearfield |  |  |  | 0.2
BD 2466-2 | TRAVIS | Clearfield | Brisbin |  |  |  | 0.2
BD 2494-2 | SOBIEN | Allegheny | Monroeville |  |  |  | 1
BD 2494-3 | SOBIEN | Allegheny | Monroeville |  |  |  | 1
BD 2494-4 | SOBIEN | Allegheny | Monroeville |  |  |  | 1
BD 2529 | HOSTEIN | Allegheny | Wilkins |  |  |  | 0.3
BD 2533-6 | CIRCOLO FEBO | Allegheny | Plum |  |  |  | 0.2
BD 2579 | BLAKE | Armstrong | Kiskiminetas |  |  |  | 0.2
BD 2607 | BD 2607 | Cambria | Susquehanna |  |  |  | 0.1
BD 2666-1 | AME ZION CHURCH MINE DRAINAGE | Allegheny | Pittsburgh (D) |  |  |  | 0
BD 2694 | TORCHIA MINE DRAINAGE | Lawrence | Neshannock |  |  |  | 0.2
BD 2694-01 | TORCHIA MINE DRAINAGE | Lawrence | Neshannock |  |  |  | 0.2
BD 2697-1 | KASCAK MINE DRAINAGE | Allegheny | Kennedy |  |  |  | 0.2
BD 2701 | PURDY MINE DRAINAGE | Allegheny | Wilkins |  |  |  | 0.2
BD 2702 | LORELLI MINE DRAINAGE | Jefferson | McCalmont |  |  |  | 0.2
BD 2707-1 | BD 2707-1 | Clearfield | Huston |  |  |  | 0
BD 2712 | ABANDONED SURFACE MINE | Clearfield | Bigler |  |  |  | 3
BD 2715 | BONE MINE DRAINAGE | Allegheny | Wilkins |  |  |  | 0.2
BD 2718 | GORNATTI | Elk | Fox |  |  |  | 0
BD 2721 | KITCHEN MINE DRAINAGE | Clarion | Piney |  |  |  | 0.2
BD 2722 | MAMAU MINE SUBSIDENCE | Indiana | Grant |  |  |  | 0
BD 2723 | TUCKER | Allegheny | Penn Hills |  |  |  | 0
BD 2725 | FIFTH AVENUE TR 300 | Clearfield | Woodward |  |  |  | 0
BD 2726 | MINE DRAINAGE | Clearfield | Decatur |  |  |  | 0
BD 2727 | LOUIS GRAHAM | Clearfield | Bradford |  |  |  | 0
BD 2728 | YAVORSKY | Clearfield | Gulich |  |  |  | 0
BD 2729 | FESS SUBSIDENCE | Indiana | Center |  |  |  | 0
BD 2730 | FELTON SUBSIDENCE | Westmoreland | Unity |  |  |  | 0
BD 2731 | KLUCHUROSKY MINE DRAINAGE | Indiana | Green |  |  |  | 0
BD 2732 | DAWSON MINE SUBSIDENCE | Westmoreland | Unity |  |  |  | 0
BD 2733 | MCGHEE MINE DRAINAGE | Allegheny | Churchill |  |  |  | 0
BD 2734 | MINE DRAINAGE | Centre | Snow Shoe |  |  |  | 0.2
BD 2736 | HUBNER MINE DRAINAGE | Allegheny | Plum |  |  |  | 0
BD 2738 | MELANDER DRAINAGE | Clearfield | Bigler |  |  |  | 0
BD 2741 | RISHER MINE | Allegheny | West Mifflin |  |  |  | 0
BD 2744 | PATTERSON MINE DRAINAGE | Allegheny | Penn Hills |  |  |  | 0
BD 2745 | MINE DRAINAGE | Allegheny | Carnegie |  |  |  | 0
BD 2757-1 | CRAWFORD | Allegheny | Pittsburgh (D) |  |  |  | 0.3
BD 2760 | TOURNAY MINE DRAINAGE | Allegheny | McDonald |  |  |  | 0
BD 2762 | TOTH MINE DRAINAGE | Allegheny | Munhall |  |  |  | 0.2
BD INQ 04-10-605 | KARWOWSKI MINE DRAINAGE | Allegheny | Collier |  |  |  | 0.2
BD INQ 04-10-623 | NESHANNOCK II (SHENANGO ROAD) | Lawrence | Neshannock |  |  |  | 0
BD INQ 04-11-646 | COLLINGWOOD SUBSIDENCE | Somerset | Stonycreek |  |  |  | 0
BD INQ 05-01-016 | COLLINS SUBSIDENCE | Washington | Smith |  |  |  | 0
BD PA 0028 | ST. NORBERT'S | Allegheny | Pittsburgh (D) |  |  |  | 0.5
BD PA 0040 | FOLINO | Washington | Robinson |  |  |  | 0.5
BD PA 0085 | LITZINGER | Clearfield |  |  |  |  | 0.3
BD PA 0172 | SMITH-BUFFLEHEAD | Fayette | Dunbar |  |  |  | 0.5
BD PA 0250 | COMMONWEALTH LAND | Somerset | Jenner |  |  |  | 0.3
BD PA 0301 | SQUIZ, INC. | Butler | Buffalo |  |  |  | 0.4
BD PA 0360 | CHEPPA | Allegheny | Churchill |  |  |  | 0.2
BD PA 0372 | ARNOLD | Allegheny | Monroeville |  |  |  | 0.2
BD PA 0382 | MEYERS | Allegheny | Penn Hills |  |  |  | 0.3
BD PA 0459 | O'MALLEY | Allegheny |  |  |  |  | 0
BD PA 0532 | BD PA 0532 | Armstrong | Bradys Bend |  |  |  | 0
BD PA 0612 | SMITH | Armstrong | Gilpin |  |  |  | 0.2
BD PA 0655 | SENTNER | Washington | Smith |  |  |  | 0.2
BD PA 0943 | RAIMONDO | Westmoreland | Unity |  |  |  | 0.1
BD PA 1324 | HICKS | Clearfield | Brady |  |  |  | 30
BD PA 1412 | DONAHUE | Elk | Horton |  |  |  | 1
BD PA 1444 | HAUPT | Allegheny | West Mifflin |  |  |  | 0.3
BD PA 1509 | JASKOWAK | Mercer |  |  |  |  | 0.5
BD PA 1563 | GREENLEAF STREET | Allegheny | Pittsburgh (D) |  |  |  | 0.6
BD PA 1570 | BD PA 1570 | Allegheny | Pittsburgh (D) |  |  |  | 0.25
BD PA 1582 | CONFINI | Allegheny |  |  |  |  | 1
BD PA 1657 | MAZEROV | Allegheny | Churchill |  |  |  | 0.4
BD PA 1704 | JENKINS | Allegheny | West Mifflin |  |  |  | 0.3
BD PA 1710 | DAUTOVICH | Allegheny | Plum |  |  |  | 0
BD PA 1712 | MINE DRAINAGE | Allegheny | Plum |  |  |  | 0
BD PA 1720 | RAMEY | Allegheny | South Park |  |  |  | 0.5
BD PA 1865 | CRISSMON MO | Armstrong | Rayburn |  |  |  | 1
BD PA 1898 | TEMPALSKI | Allegheny |  |  |  |  | 0.3
BD PA 2083 | DODSON | Bedford | Broad Top |  |  |  | 3
BD PA 2129 | SHORT | Clearfield | Chester Hill |  |  |  | 0.2
BD PA 2491 | CHUCKALOVCAK | Cambria | Summerhill |  |  |  | 0.5
BD PA 2514 | SANNER | Somerset | Southampton |  |  |  | 1
BD PA 2534 | EXPORT | Westmoreland | Export |  |  |  | 1
BD PA 2543 | NORTH IRWIN DEV. CORP. | Westmoreland | North Irwin |  |  |  | 1
BD PA 2555 | DYSON MINE OPENING | Westmoreland | South Huntingdon |  |  |  | 0.1
BD PA 2574 | WEST MOSHANNON N. (89) | Clearfield | Woodward |  |  |  | 0.25
BD PA 2575 | GLASS CITY S.W. | Centre | Rush |  |  |  | 0
BD PA 2707 | DESTEPHANO | Elk | Benzinger |  |  |  | 0.5
BD PA 2711 | DOBSON | Cambria | Scalp Level |  |  |  | 1
BD PA 2736 | EPPS | Fayette | Menallen |  |  |  | 0.2
BD PA 2790 | MARSHALL | Washington | Allenport |  |  |  | 1
BD PA 2792 | KOZEL | Fayette |  |  |  |  | 0.1
BD PA 3077 | ANKENY | Somerset | Jenner |  |  |  | 0.25
BD PA 3244 | MINE SUBSIDENCE | Indiana | Center |  |  |  | 0.2
BD PA 3265 | DUNKARD TOWNSHIP | Greene | Dunkard |  |  |  | 0.1
BD PA 3331 | DISTANT NORTH | Armstrong | Mahoning |  |  |  | 0.5
BD PA 3403 | BD PA 3403 | Westmoreland | Arnold |  |  |  | 0.5
BD PA 3419 | BEAGLE CLUB | Lawrence | Wilmington |  |  |  | 0.5
BD PA 3561 | GROCE | Clarion | Elk |  |  |  | 0.5
BD PA 3783 | HOOVERVILLE SOUTH | Westmoreland |  |  |  |  | 0.2
BD PA 3797 | HILLIS | Butler |  |  |  |  | 2
BD PA 3956 | ROBERTS MINE SHAFT | Jefferson | Bell |  |  |  | 0.2
BD PA 4357 | BONGIANINO | Indiana | Blairsville |  |  |  | 0.1
BD PA 4377 | BAILEY | Cambria | Scalp Level |  |  |  | 0.5
BD PA 4383* | DIANA | Allegheny | Penn Hills |  |  |  | 2
BD PA 4520 | HASSINGER | Centre | Rush |  |  |  | 0.2
BD PA 4526 | PRESTASH | Clearfield | Morris |  |  |  | 0.2
BD PA 4529 | ARSENICH | Clearfield | Morris |  |  |  | 1
BD PA 4684 | CHIPPS | Greene | Dunkard |  |  |  | 1
BD PA 4717 | MOSKO | Westmoreland | Derry |  |  |  | 0.2
BD PA 4748 | GRIMES | Washington | California |  |  |  | 1
BD PA 4751 | SUSTRICK | Washington | West Pike Run |  |  |  | 0.5
BD PA 4760 | SPERANZA | Indiana | Young |  |  |  | 0.1
BD PA 6598 | McFADDEN WATER SUPPLY | Butler | Venango |  |  |  | 9.5
BD PA 6742 | KRIEBEL | Clarion | Piney |  |  |  | 0.5
BD PA 6766 | BUSSARD | Bedford | Broad Top |  |  |  | 0
BD PA 6802 | HUDISH | Clearfield | Cooper |  |  |  | 0.3
BD PA 6886 | BD PA 6886 | Clearfield | Bloom |  |  |  | 0.2
BD PA 7004 | MAHONEY | Clearfield | Clearfield |  |  |  | 0.5
BD PA 7066 | LANSBERRY | Clearfield | Bradford |  |  |  | 0.5
BD PA 7103 | HOOVER | Clearfield | Decatur |  |  |  | 0.5
BD PA 7162 | LANSBERRY | Clearfield | Bradford |  |  |  | 1
BD PA 8506 | STONER | Somerset |  |  |  |  | 0.2
BF 392-102.1 | GLENN COAL CO. | Jefferson | Oliver |  |  |  | 0
BF 396-102.1 | THOMAS A. FELLO | Indiana | Conemaugh |  |  |  | 0
BF 405-101.1 | RUSSELL JOKI (I) (CONSULT. DESIGN) | Washington | Union |  |  |  | 37
BF 445-102.1 | GLACIAL MINERALS, INC. (STRATTANVILLE) | Clarion | Clarion |  |  | 2006-04-25 | 15
BF 445-103.1 | GLACIAL MINERALS, INC. (REED) | Clarion | Clarion |  |  | 2006-04-25 | 8
BF 461-101.1 | CAMBRIA MILLS COMPANY | Clearfield | Beccaria |  |  |  | 0
BF 465-101.1 | PENGROVE COAL COMPANY(EAKIN) | Venango | Clinton |  |  | 2006-12-30 | 23.5
BF 468 | PENGROVE COAL COMPANY(RUTH) | Butler | Venango |  |  |  | 0
BF 483-101.1 | RONDELL-CORREAL (NEWMYER RUN) PHASE I | Fayette | Saltlick |  |  | 2006-07-25 | 47
BF 484-101.1 | BRYAR CONSTRUCTION | Westmoreland | Hempfield |  |  |  | 0
BF 487-101.1 | HAMILTON BROTHERS COAL, INC. | Clearfield | Beccaria |  |  | 2005-11-30 | 33
BF 499-101.1 (ACT 181) | H & D COAL COMPANY(H&D #8) | Venango | Irwin |  |  | 2005-12-15 | 7
BF 500-101.1 | PENGROVE COAL COMPANY(MARTIN BELL) | Venango | Clinton |  |  |  | 0
BF 508-101.1 | EBONY COAL COMPANY | Westmoreland | Penn |  |  | 2006-05-30 | 26
BF 516-101.1 | GLACIAL MINERALS, INC. | Venango | Richland |  |  |  | 0
BF 517-101.1 | GLACIAL MINERALS, INC. | Clarion | Porter |  |  |  | 0
BF 518-101.1 | GLACIAL MINERALS, INC. | Clarion | Richland |  |  |  | 0
BF 519-101.1 | GLACIAL MINERALS, INC. | Clarion | Monroe |  |  |  | 0
BF 520-101.1 | BENJAMIN COAL CO. | Clearfield | Brady |  |  |  | 0
CRF 002-101.1 | WEST NEWTON COAL LOGISTICS CO. | Westmoreland | Rostraver
DMF 002-104.1 | DARMAC ASSOCIATES CORP. | Butler | Oakland |  |  |  | 0
DMF 013-139.1 | DOVERSPIKE BROTHERS COAL, CO.-DORA #6 | Jefferson | Perry |  |  | 2006-08-30 | 1
DMF 013-140.1 | DOVERSPIKE BROTHERS COAL, CO.-DORA #6 | Jefferson | Perry |  |  | 2006-07-25 | 8
NCF 006-101.1 | BUCKEYE WRECKING & TRANSFER, INC. | Westmoreland | Vandergrift |  |  | 2006-08-29 | 7
OSM 02(0275)101.1 | KARAFFA MINE DRAINAGE | Allegheny | Port Vue |  |  |  | 0
OSM 02(0350,0351)101.1 | IMPERIAL NORTH/CLINTON SOUTHEAST | Allegheny | Findlay |  |  |  | 0
OSM 02(2602)101.1 | LG.MINE FIRE (TEPE PUMP STA.) | Allegheny | Jefferson Hills |  |  |  | 100
OSM 02(4422)102.1 | FISHING RUN (GD050121) | Allegheny | South Fayette |  |  | 2005-11-01 | 0
OSM 03(1574)101.1 | SLABTOWN NORTHWEST | Armstrong | Boggs |  |  | 2006-06-02 | 14
OSM 03(2973)101.1 | TIDAL NORTHEAST | Armstrong | Madison |  |  |  | 0
OSM 03(3359)101.1 | GOHEENVILLE N.E. (MAHONING LAKE) | Armstrong | Wayne |  |  |  | 0
OSM 03(3498)101.1 | CHARLESTOWN SOUTHWEST | Armstrong | Redbank |  |  |  | 0
OSM 04(6279)101.1 | MISKITA LAKE FAR SOUTHWEST | Beaver | South Beaver |  |  |  | 0
OSM 10(0674)101.1 | SLIPPERY ROCK SOUTH | Butler | Slippery Rock |  |  | 2006-02-28 | 21
OSM 10(0752)101.1 | SHERWIN NORTH | Butler | Clay |  |  |  | 0
OSM 10(0760)101.1 | FINDLAY RUN WEST | Butler | Cherry |  |  | 2006-02-15 | 20
OSM 10(2922)101.1 | COALTOWN SOUTH | Butler | Cherry |  |  |  | 0
OSM 10(3917)101.1 | DENNYS MILLS NORTH | Butler | Winfield |  |  | 2006-04-15 | 9
OSM 10(6493)101.1 | WEST LIBERTY EAST #3 | Butler | West Liberty |  |  | 2007-02-28 | 5
OSM 10(6592)101.1 | CHERRY VALLEY SOUTH | Butler | Cherry Valley |  |  |  | 0
OSM 10(7000)101.1 | EAU CLAIRE SOUTHWEST | Butler | Allegheny |  |  |  | 4
OSM 10(7138)101.1 | WHISKERVILLE WEST | Butler | Washington |  |  |  | 0
OSM 11(2810)101.1 | SLATE LICK RUN EAST | Cambria | White |  |  |  | 0
OSM 11(4789)101.1 | WYEROUGH RUN NORTH | Cambria | Chest |  |  |  | 32
OSM 13(3216)101.1 | SPRING MOUNTAIN | Carbon | Packer |  |  | 2005-11-30 | 13.5
OSM 13(4653)101.1 | NESQUEHONING SOUTHWEST | Carbon | Nesquehoning |  |  | 2006-02-01 | 17
OSM 13,40(3204)101.1 | BEAVER BROOK | Carbon | Banks |  |  |  | 0
OSM 14(0883)101.1 | ORVISTON | Centre | Curtin |  |  | 2007-05-30 | 17
OSM 14(6818)101.1 | PINE GLEN SOUTHEAST | Centre | Burnside |  |  |  | 0
OSM 16(0992)101.1 | SOUTH OF SHAMBURG | Clarion | Piney |  |  | 2006-02-28 | 14
OSM 16(2826)101.1 | FAIRMOUNT CITY (CONSULT.DESIGNED) | Clarion | Redbank |  |  |  | 0
OSM 16(6049)101.1 | ST. NICHOLAS CEMETERY EAST | Clarion | Limestone |  |  | 2006-11-28 | 3
OSM 16(6204)101.1 | UNKNOWN MAPLE GROVE | Clarion | Madison |  |  | 2006-07-30 | 82
OSM 16(6700)101.1 | CLARION LIMESTONE HS NW | Clarion | Clarion |  |  | 2006-12-19 | 33
OSM 17(0115)101.1 | SANDY CREEK #1 | Clearfield | Covington |  |  | 2006-09-26 | 22
OSM 17(1395)101.1 | GRAMPIAN | Clearfield | Penn |  |  | 2006-05-30 | 34
OSM 17(1946)101.1 | DRANE | Clearfield | Decatur |  |  |  | 0
OSM 17(2998)101.1 | NEEDFUL SOUTH NO. 1 | Clearfield | Bradford |  |  |  | 62
OSM 17(3992)101.1 | STUMPTOWN NORTH | Clearfield | Decatur |  |  |  | 0
OSM 17(4454)102.1 | BCI WATERLINE AREA A (GA) | Clearfield | Beccaria |  |  |  | 0
OSM 17(4537)101.1 | ALBERT LANDING FIELD SOUTH | Clearfield | Morris |  |  |  | 22
OSM 17(4544,4545)101.1 | ALDER RUN WEST | Clearfield | Morris |  |  |  | 92
OSM 17(6801)101.1 | GRASSFLAT NORTHWEST | Clearfield | Cooper |  |  | 2006-09-30 | 203
OSM 17(7004)102.1 | OWENS CEMETERY | Clearfield | Clearfield |  |  |  | 1.5
OSM 17(7086)101.1 | BLUEBALL EAST | Clearfield | Morris |  |  | 2006-11-30 | 25
OSM 17(7163)101.1 | McDOWELL MOUNTAIN SOUTH | Clearfield | Bradford |  |  | 2005-11-15 | 58
OSM 17(7180)101.1 | GOSHEN SOUTH SITE | Clearfield | Goshen |  |  | 2006-08-30
OSM 19(4032)101.1 | ARISTES EAST | Columbia | Conyngham |  |  |  | 0
OSM 24(3888)101.1 | DARK HOLLOW | Elk | Benezette |  |  |  | 0
OSM 24(3890)101.1 | DENTS RUN | Elk | Benezette |  |  |  | 0
OSM 24(3897)101.1 | PORCUPINE HOLLOW I | Elk | Benezette |  |  |  | 0
OSM 24(3898)101.1 | PORCUPINE HOLLOW II | Elk | Benezette |  |  | 2006-04-15 | 47
OSM 26(0149)101.1 | LINDA WEAVER SUBSIDENCE | Fayette | Upper Tyrone |  |  |  | 0
OSM 26(1821)101.1 | NAOMI EAST (CONSULT.DESIGNED) | Fayette | Washington |  |  |  | 0
OSM 26(2718)104.1 | PERCY MINE FIRE | Fayette | North Union |  |  |  | 0
OSM 32(2425)102.1 | LAUREL RUN PHASE 2 (GA) | Indiana | Brush Valley |  |  |  | 8
OSM 35(1524)102.1 | GRASSY ISLAND CREEK | Lackawanna | Archbald |  |  | 2005-12-31 | 116.5
OSM 35(2078)102.1 | EDDY CREEK (SEE 101.1 - COMBINED) | Lackawanna | Olyphant |  |  | 2006-04-30 | 20
OSM 35(2179)103.1 | TAYLOR SOUTH MAIN | Lackawanna | Taylor |  |  |  | 0
OSM 35(2185)102.1 | KEYSER AVENUE/SCRANTON | Lackawanna | Scranton |  |  |  | 2
OSM 35(3735)102.1 | GREENWOOD | Lackawanna | Moosic |  |  | 2006-03-31 | 20.9
OSM 35(3738)102.1 | NORTH GOLF COURSE | Lackawanna | Taylor |  |  |  | 0
OSM 35(3742)201.1 | GRASSY ISLAND | Lackawanna | Olyphant |  |  | 2006-03-01 | 61.7
OSM 35(4190)101.1 | INTERCHANGE 56 SOUTH | Lackawanna | Scranton |  |  |  | 25
OSM 37(4481)101.1 | DUCKRUN EAST | Lawrence | Wayne |  |  | 2006-10-30 | 6
OSM 37(4489)101.1 | MARTIN ROAD | Lawrence | Slippery Rock |  |  | 2007-01-30 | 85
OSM 40(0493)101.1 | HOLLARS HILL SOUTH | Luzerne | Hazle |  |  | 2006-08-30 | 239.5
OSM 40(1365)101.1 | HAZLETON S.C. WEST | Luzerne | Hazleton |  |  |  | 77
OSM 40(1372,1374)101.1 | HUMBOLDT S.W. | Luzerne | Hazle |  |  | 2006-06-30 | 106.3
OSM 40(1381)101.1 | FREELAND SOUTH | Luzerne | Hazle |  |  |  | 15
OSM 40(1859)101.1 | LAUREL RUN CREEK (PARSONS) | Luzerne | Wilkes-Barre |  |  |  | 1
OSM 40(2132)102.1 | PINE CREEK RESERVOIR | Luzerne | Wilkes-Barre |  |  |  | 3
OSM 40(2165)101.1 | HILLDALE | Luzerne | Plains |  |  | 2005-12-31 | 32
OSM 40(3044)101.1 | FERN GLEN | Luzerne |  |  |  | 2006-08-31 | 100
OSM 40(3217)101.1 | DRIFTON | Luzerne | Hazle |  |  |  | 15
OSM 40(3725)101.1 | HOLLARS HILL | Luzerne | Hazle |  |  | 2005-11-30 | 141.1
OSM 40(3734)101.1 | WEST SUSCON | Luzerne | Jenkins |  |  | 2005-10-30 | 127.9
OSM 43(4284)101.1 | NESBIT CORNERS EAST | Mercer | Worth |  |  | 2006-01-01 | 23
OSM 54(1002,4044)101.1 | GIRARDVILLE EAST | Schuylkill | Girardville |  |  | 2005-12-31 | 0
OSM 54(2025)103.1 | PALO ALTO NORTH | Schuylkill | Palo Alto |  |  | 2006-01-15 | 0
OSM 54(2029)101.1 | DONALDSON | Schuylkill |  |  |  |  | 26
OSM 54(3042)102.1 | ONEIDA WEST | Schuylkill | North Union |  |  | 2005-12-31 | 351
OSM 54(3046)101.1 | GREENE MTN. S. | Schuylkill | East Union |  |  | 2005-12-31 | 128
OSM 54(3630)101.1 | PINE HILL NORTH | Schuylkill | Cass |  |  | 2005-03-01 | 250
OSM 54(3633)103.1 | MOUNT PLEASANT | Schuylkill | Foster |  |  | 2006-02-28 | 43
OSM 54(3649)102.1 | NEWTOWN SOUTH 2 | Schuylkill | Reilly |  |  | 2005-06-30 | 50
OSM 54(3703)104.1 | NORTH DONALDSON | Schuylkill | Frailey |  |  | 2006-04-30 | 25
OSM 54(3727)101.1 | NORTH SHEPPTON | Schuylkill | East Union |  |  | 2007-12-31 | 120
OSM 54(4208)102.1 | ROBINSON | Schuylkill | Frailey |  |  |  | 1.5
OSM 54(4666)201.1 | LITTLE WOLF CREEK | Schuylkill | East Norwegian |  |  | 2005-09-30 | 268.2
OSM 56(0783)101.1 | BROTHERTON NORTH | Somerset |  |  |  |  | 0
OSM 61(2906)101.1 | WOODS CORNERS | Venango | Irwin |  |  | 2006-05-30 | 20
OSM 61(6942)101.1 | EMLENTON WEST | Venango | Scrubgrass |  |  | 2006-02-28 | 32
Future Awards: |  | 284 | Contracts |  |  |  | 4499.85 | 72817964.06 | 16880858.99 | 1287080 | 3673227.9 | 0 | 0 | 861358.81 | 32400.22 | 1300000